## Sheet1
Risk | Risk Statement | Response Strategy | Objectives | Likelihood | Impact | Risk Level
Database SQL Injection | SQL Injection can manipulate data. It can lead to Data leake/Complete Data loss | Refactor the code to make SQL injection as harder as possible/ Stronger password protection with MFA enablen/ Use a seperate VM for the database. | Sanitise data entry so that SQL injection can not be performed without database access. | Medium | High | 9
File Corruptions | File can get corrupted during transfer to the client side. It will cause application to go offline or unresponsive. | Have multiple local and remote copies of the application. | Provide multiple copies on local and on remote. | Medium | Low | 2
Connection/Internet Failure | Could lead to a problem when pushing codes to repo. This means that software becomes diffucult to acquire. | Have an alternative methods of connection to the internet like a mobile hotspot etc in terms of an internet connection failure. | It will reduce the time spent being offline due to conneciton issues or in case of an internet provider. | Low | Medium | 4
Hardware failure | Lost work and inability to complete the project on time. | Inform trainers with the issue and keep regular remote pushing to latest changes to recover the software from remote. | it will cause a major issue but this can be resolved by pushing regulary to remote repositories. | Low | High | 8
Time mismanagement | It can be diffucult to track and manage the time when working in a project like this considering the timeframe we are giving. | Making sure using story point and time tracking on the Jira Kanan board will lead to better time management when developing this project | To reduce time spent on less important tasks and deliver the project in a complete state and on time. | Medium | High | 9
Protection of the data that has been pushed to Remote (Github) | Any source of code pushed to Github could potentially contain information that hackers can use when trying to attack the application. This can result of data being leaked or application taking offline. | Use stronger hashed passwords and username. Keep updating them regulary. | It will reduce the likelihood of hacking adn data leaks. | High | Low | 3
Bootstrap link unavailability | Bootstrap CDN are used to deliver the online content. There is a chance of version update or version gets no longer supported. | I will download the version of the bootstrap files used to create this application so that they can be readily available at all times. | I will migitate the effects of the Bootstrap CDN outage for the required project files. | Low | High | 8